# Business Requirements Document (BRD)

Project Name: Zydus CareConnect — Omnichannel Hospital Appointment Booking & Queue Optimization System

Organization: Zydus Hospitals (Hypothetical Pan-India Multispecialty Network Case Study)

Document Version: 2.1 (BABOK v3 Aligned Portfolio Draft — Proposed for Validation)

Lead Business Analyst: Shruti Thacker (@shrutithacker14)

# 1. Executive Summary & Business Problem

For this hypothetical business analysis case study, Zydus Hospitals is modeled across 7 multispecialty units in 6 regional markets (Gujarat [Ahmedabad & Bhuj], Maharashtra [Mumbai], Rajasthan [Jaipur], Delhi NCR [New Delhi], Karnataka [Bengaluru], and Tamil Nadu [Chennai]), handling an assumed baseline volume of approximately 1,250 Outpatient Department (OPD) consultations daily. The scenario models a transition from decentralized telephone lines, physical registers, and standalone spreadsheets to a centralized omnichannel appointment and queue management platform.

23.92% synthetic no-show share (As-Is): 598 of 2,500 baseline records are marked No-Show (accounting for ₹4,45,250 in simulated unbilled slot value), compared to 7.28% (182 of 2,500; ₹1,39,700) in the To-Be cohort.

11.36-minute mean booking turnaround (As-Is): Baseline bookings via Phone Call (60.40%) and Walk-In Desk (39.60%) average 11.36 minutes, compared to 1.79 minutes across the omnichannel To-Be cohort.

14.76% double-booking conflict share (As-Is): 369 baseline bookings experienced concurrent slot conflicts, contributing to a 48.52-minute mean OPD waiting hall time for completed visits (reduced to 14.25 minutes in the To-Be cohort).

4.83% cancelled slot refill rate (As-Is): Only 18 of 373 cancelled baseline appointments were manually reallocated, compared to 78.17% (154 of 197) in the To-Be cohort with automated waitlist promotion.

# 2. Business Objectives & Target KPIs

| KPI ID | KPI Metric | Baseline (As-Is) | Target (To-Be) | To-Be Sample | Validation Approach |
| --- | --- | --- | --- | --- | --- |
| KPI-01 | OPD No-Show Share | 23.92% (598/2,500) | < 8.0% | 7.28% (182/2,500) | 90-day pilot vs. matched baseline |
| KPI-02 | Mean Booking Turnaround | 11.36 min | < 2.0 min | 1.79 min | System timestamp log audit |
| KPI-03 | Double-Booking Conflicts | 14.76% (369/2,500) | 0.0% | 0.00% (0/2,500) | Redis 300s lock concurrency test |
| KPI-04 | Digital Self-Service Share | 0.00% (0/2,500) | >= 70.0% | 74.04% (1,851/2,500) | App + Web + WhatsApp Bot share |
| KPI-05 | Cancelled Slot Re-Fill Rate | 4.83% (18/373) | >= 75.0% | 78.17% (154/197) | Waitlist refills / total cancelled |
| KPI-06 | Waiting Time (Completed) | 48.52 min | < 15.0 min | 14.25 min | QR check-in to consult start |
| KPI-07 | ABHA ID Linkage Rate | 18.08% (452/2,500) | >= 80.0% | 84.08% (2,102/2,500) | Verified ABDM profile linkage |

# 3. Functional Requirements Summary (FR-01 to FR-12)

| Req ID | Module | Requirement Description | Priority | Story / UAT |
| --- | --- | --- | --- | --- |
| FR-01 | Patient Auth & UHID | Authenticate via Mobile OTP; auto-link Zydus UHID (ZYD-UHID-XXXXXX) and ABHA ID. | Must Have | US-01 / TC-01 |
| FR-02 | Multi-Filter Discovery | Filter by Zydus State Facility, Specialty, Doctor, Fee (₹), Language, and Live Slots. | Must Have | US-01, US-03 / TC-01, TC-04 |
| FR-03 | Concurrency Slot Lock | Place a 5-minute (300s) Redis lock on selected slots during checkout. | Must Have | US-02 / TC-02, TC-03 |
| FR-04 | Self-Service Reschedule | Allow 1-click rescheduling up to 2 hours prior via Web, App, or WhatsApp at ₹0 fee. | Must Have | US-03, US-04 / TC-05, TC-06 |
| FR-05 | Cancellation & Refund | Instant 100% UPI refund for cancellations >= 4h prior; 20% fee for < 4h. | Must Have | US-05 / TC-07, TC-08 |
| FR-06 | Smart Reminders | Automated WhatsApp & SMS alerts at booking, T-24h, and T-2h with quick-reply buttons. | Must Have | US-06 / TC-09 |
| FR-07 | Dynamic Waitlist | Auto-notify top 3 waitlisted patients on cancellation; 15-min claim window. | Should Have | US-07 / TC-10 |
| FR-08 | Doctor Leave & Roster | Allow doctors to mark emergency OT/leave and trigger bulk priority reschedule links. | Must Have | US-08 / TC-11 |
| FR-09 | Assisted Desk Console | Unified reception console for walk-ins, Cash/UPI payment, and <45s QR token printing. | Must Have | US-09 / TC-12 |
| FR-10 | QR Express Check-In | Self-service lobby QR scan within 45 mins of slot to generate live OPD queue token. | Should Have | US-10 / TC-12 |
| FR-11 | Tele-Consultation | Option to toggle Video Tele-Consultation with encrypted WebRTC link & e-prescription. | Could Have | US-11 / TC-13 |
| FR-12 | Executive BI Analytics | Real-time dashboard tracking all 7 Zydus units, Revenue (₹), No-Show %, and Channel Mix. | Must Have | US-12 / TC-14 |

# 4. Non-Functional Requirements (NFR)

NFR-01 (Performance): API response < 1.2s (P95) under 5,000 concurrent users during peak morning OPD traffic (08:30 AM – 11:30 AM IST).

NFR-02 (Availability): 99.95% uptime SLA with multi-AZ cloud failover and 15-minute RPO backups.

NFR-03 (Compliance & Security): Alignment with India's Digital Personal Data Protection (DPDP) Act 2023 and Ayushman Bharat Digital Mission (ABDM) health data standards; AES-256 encryption at rest and TLS 1.3 in transit.

NFR-04 (Localization): Full multilingual UI and WhatsApp Bot support in English, Hindi (हिंदी), and Gujarati (ગુજરાતી).

# 5. Portfolio Case-Study Disclaimer

This repository presents a hypothetical Business Analysis portfolio case study modeled around Zydus Hospitals. It is not commissioned, endorsed, or supplied by Zydus Hospitals, and contains zero real patient or operational records. All metrics are calculated from the 5,000-row synthetic dataset constructed to demonstrate BABOK-aligned requirements engineering, process modeling, backlog refinement, UAT planning, and KPI analysis.