## Stakeholder_Register
ZYDUS HOSPITALS (HYPOTHETICAL CASE STUDY) — STAKEHOLDER REGISTER & MENDELOW MATRIX
Role-Based Stakeholder Personas Across 7 Regional Zydus Units ¦ Lead Business Analyst: Shruti Thacker (@shrutithacker14)
Stakeholder ID | Stakeholder Role / Persona | Category | Power / Influence | Interest Level | Mendelow Quadrant | Primary Pain Points (As-Is Cohort) | Key Expectations (To-Be Solution) | Engagement & Communication Strategy
SH-01 | Patients & Family Caregivers (Urban & Regional) | External | Medium | High | Keep Informed | 11.36-minute mean booking turnaround in the synthetic sample; zero automated reminders; unable to reschedule without calling busy reception lines. | 24/7 self-service booking via Zydus App/Web/WhatsApp in English, Hindi & Gujarati; instant UPI refund on cancellation >=4h prior. | Post-OPD CSAT feedback loops, multilingual in-clinic QR standees, WhatsApp onboarding guides.
SH-02 | Zydus Front-Desk Receptionists & OPD Billing Staff | Internal - Operational | Low | High | Keep Informed | High volume of manual phone bookings (60.40% of As-Is volume); patient escalations caused by 14.76% concurrent double-booking conflicts. | Single-screen unified Zydus reception console; automated T-24h/T-2h reminders; <45-second walk-in QR token printing. | Hands-on UAT sandbox workshops, shift-champion training, SOP quick-reference desk cards.
SH-03 | Zydus OPD Consulting Doctors & Visiting Specialists | Internal - Clinical | High | High | Manage Closely | 23.92% synthetic no-show share leaves unutilized clinical slots; unannounced walk-ins and double bookings disrupt OPD consultation rhythm. | Predictable daily OPD schedule; mobile doctor app to mark emergency OT/leave with 1-click bulk patient rescheduling. | Bi-weekly Clinical Advisory demos; 1-on-1 specialty roster configuration sign-off.
SH-04 | OPD Floor Nursing & Queue Coordinators | Internal - Operational | Medium | High | Keep Informed | 48.52-minute mean waiting hall delay among completed visits in the As-Is sample; constant manual inquiries outside consultation rooms. | Live OPD token display integration; lobby QR express check-in alerts when patient arrives within 45 minutes of slot. | Weekly OPD floor-walk simulations and queue token dry runs.
SH-05 | Zydus Hospitals Medical Director & COO | Internal - Executive | High | High | Manage Closely | OPD capacity leakage (₹4,45,250 simulated no-show loss in sample) and low baseline patient CSAT (2.61 / 5.00). | Reduce OPD no-shows <8.0%, achieve >=70% digital self-service adoption, and monitor all 7 regional units via live BI dashboard. | Bi-weekly Executive Steering Committee KPI & milestone briefings.
SH-06 | Zydus Hospital IT & HIS Architecture Team | Internal - Technical | High | Medium | Keep Satisfied | Fragmented local spreadsheets and legacy HIS sync lag causing slot conflicts across multi-state hospital units. | HL7/FHIR REST APIs, Redis 300-second concurrency slot locking, 99.95% uptime SLA with zero impact on core IPD/Billing servers. | Weekly Architecture Review Board (ARB) & API contract sign-offs.
SH-07 | Finance & Revenue Reconciliation Team | Internal - Governance | Medium | Medium | Monitor | High manual cash handling at OPD counters (64.36% in As-Is) and disputed late-cancellation refunds. | Automated T+1 Razorpay/UPI settlement ledger synced with Zydus HIS billing codes and configurable 4-hour refund rules. | Monthly automated reconciliation test reports during UAT phase.
SH-08 | Data Privacy & ABDM Compliance Officer | Internal - Governance | High | Low | Keep Satisfied | Low baseline ABHA ID linkage (18.08% in As-Is) and unencrypted patient details in standalone desk spreadsheets. | DPDP Act 2023 consent logging, verified ABHA ID linkage (>=80% target), and AES-256 / TLS 1.3 encryption controls. | Formal Data Protection Impact Assessment (DPIA) & security audit sign-off prior to Go-Live.

## RACI_Matrix
ZYDUS HOSPITALS (HYPOTHETICAL) — RACI GOVERNANCE MATRIX (R = Responsible, A = Accountable, C = Consulted, I = Informed)
BABOK v3 Aligned Governance Model Across Discovery, Analysis, Design, Testing & Phased Rollout
Deliverable / Project Activity | Project Phase | Lead Business Analyst (Shruti Thacker) | Zydus COO / Project Sponsor | OPD Clinical Lead | Front-Desk Supervisor | HIS / IT Architect | QA & UAT Lead
As-Is OPD Process Discovery & Synthetic Cohort Audit | Discovery | R | A | C | C | I | I
Stakeholder Analysis & Regional Pain-Point Workshops | Discovery | R | A | C | C | C | I
Business Requirements Document (BRD v2.1) & KPIs | Analysis | R | A | C | C | C | C
To-Be Omnichannel Workflow & Waitlist Algorithm Rules | Design | R | A | C | C | R | I
Agile Epics, User Stories (US-01 to US-12) & Gherkin AC | Design | R | I | C | C | C | C
HIS HL7/FHIR API, Redis Slot Lock & UPI Integration | Development | C | I | I | I | R / A | C
UAT Test Plan (UAT-TC-01 to TC-14) & RTM Verification | Testing | A | I | C | R | C | R
Front-Desk Staff Training & Phased 7-Unit State Rollout | Deployment | R | A | I | R | C | I